CRL-CW Research Project Plan

Continual reinforcement learning with reusable policy guidance in Meta-World

Project: crl_cw

Benchmark: Meta-World v3, fixed CW10 task order, full observations

Final method: To be determined through staged experiments and ablation studies

Status: Implementation and pilot validation

Updated: 2026-07-23

# 1. Research Abstract

This project studies continual reinforcement learning (CRL) for sequential robotic manipulation. The central question is whether policies learned on earlier tasks can be reused as temporary guides to improve exploration and forward transfer on a new task, while the current learner ultimately becomes independent and retains performance across the task sequence.

The experimental platform uses Meta-World v3 with the fixed CW10 order, full modern observations, Gymnasium and PyTorch SAC. The final method is intentionally not fixed at this stage. The research will first test WSRL-style warm starts and JSRL-style curricula as alternative mechanisms for forward transfer, then test task embeddings—starting with a one-hot task vector—as a mechanism for reducing forgetting. A final method will be selected or composed only after controlled ablation studies establish which components provide reliable and complementary gains.

# 2. Candidate Research Directions

## 2.1 Experimental Development Strategy

Stage A — Transfer: test wsrl_continual first, then jsrl_continual, to determine whether prior-policy guidance improves forward transfer.

Stage B — Forgetting: test task conditioning with a one-hot vector, then consider richer learned task embeddings if the simple representation is useful.

Stage C — Integration: combine only components that show complementary improvements in controlled ablations.

Stage D — Final method: define the final architecture, objective and name after evidence from transfer, forgetting and interaction ablations.

## 2.2 Candidate Transfer Mechanisms

WSRL continual:

Use the best prior policy as a fixed warm-up guide for early data collection on a new task.

Test current versus best-return parameter sources and reset versus transferred task heads.

Use this simpler mechanism as the first test of whether policy reuse improves forward transfer.

JSRL continual:

Architecture: shared actor/critic backbones with task-specific heads; task identity selects the active head but is hidden from the backbone.

Policy bank: after each task, store a complete frozen actor snapshot. The bank grows across the sequence; prior snapshots never change.

Guide selection: evaluate every prior policy on the current task and choose the policy with the highest mean current-task return.

Learner initialization: retain the current shared backbones, activate fresh task heads, reset optimizer state and clear the online replay buffer.

Mixed rollout: for each episode, the frozen guide controls the first h steps and the current SAC learner controls the remaining 200-h steps.

Curriculum: h follows 180, 160, ..., 0. Mixed-policy return is evaluated every 20k steps using a rolling window of five evaluations.

Advancement: reduce h when mixed return reaches the adaptive beta threshold (reference return with 10% tolerance), or after five evaluations without advancement.

Autonomy: the patience rule guarantees h reaches 0 by approximately 900k steps in the worst case, leaving at least approximately 100k learner-only steps in a 1M-step task.

## 2.3 Candidate Forgetting Mechanism

Start with a single-head task-conditioned SAC agent that receives the full state observation plus a one-hot task vector.

Measure whether explicit task identity improves representation separation and reduces forgetting relative to fine-tuning.

If useful, replace or augment one-hot identity with a learned task embedding or task-inference module in later ablations.

## 2.4 Intended Evaluation Semantics

During-task forward transfer: report the mixed-policy learning curve, because guide reuse is part of the proposed method.

Curriculum control: use the same mixed-policy evaluations for beta and h advancement.

Task-end performance: evaluate with h=0 (learner only).

Final average performance and forgetting: evaluate the learner heads after completing the full sequence.

Implementation note: WSRL, the frozen JSRL guide, curriculum and patience mechanism are implemented and tested as candidate variants. The output pipeline still needs to be refactored so that mixed-policy curves, rather than the current learner-only active curves, can be reported for policy-guided transfer experiments. No candidate has yet been selected as the final method.

# 3. Baselines

| Baseline | Role / definition | Status |
| --- | --- | --- |
| Single-task SAC | Independent SAC per task; reference learning curves for FT. | Running pilot |
| Fine-tuning | Single-head SAC trained sequentially with no anti-forgetting mechanism. | Implemented |
| Task-conditioned | Single-head SAC with one-hot task vector; baseline and first task-embedding ablation. | Implemented |
| PackNet | Sequential parameter pruning/freezing with task-specific masks. | Implemented; formal validation pending |
| ClonEx-SAC | Final variant: multi-head shared network, best-return exploration, episodic memory and actor behavior cloning. | Implemented; formal validation pending |
| WSRL continual | Candidate transfer mechanism: best-return frozen guide with a fixed warm-up. | Implemented; ablation pending |
| JSRL continual | Candidate transfer mechanism: best-return frozen guide with adaptive h curriculum. | Implemented; ablation pending |

# 4. Experimental Platform

| Component | Current protocol |
| --- | --- |
| Environment | Meta-World v3; full observation (not cropped to legacy 12-D) |
| Sequence | CW10: hammer, push-wall, faucet-close, push-back, stick-pull, handle-press-side, push, shelf-place, window-close, peg-unplug-side |
| Learner | PyTorch SAC; 4 x 256 hidden layers; batch 128 |
| Formal budget | 1,000,000 environment steps per task |
| Evaluation | Every 20,000 steps; formal target: 10 stochastic + 1 deterministic episodes |
| Core SAC | Replay 1M; start steps 10k; update after 1k; update frequency 50; lr 1e-3; gamma 0.99; Polyak 0.995 |
| Episode | Maximum 200 steps |
| Metrics | Average performance, average return, forgetting, forward transfer and per-task results |

# 5. Current Experiments — PILOT

The active experiment is a runtime and pipeline pilot, not a formal benchmark result. It tests whether single-task SAC can complete reliably on the local machine and produces baseline artifacts suitable for later forward-transfer calculations.

| Item | Pilot setting | Formal target |
| --- | --- | --- |
| Task coverage | First 5 CW tasks (CW5 subset) | All 10 CW10 tasks |
| Training budget | 500k steps/task | 1M steps/task |
| Seeds | Seed 0 only | At least 3 fixed seeds |
| Evaluation | 5 stochastic, 0 deterministic | 10 stochastic + 1 deterministic |
| Device | Local Apple MPS | Benchmark CPU/MPS locally; school GPU for formal runs |
| Purpose | Correctness, stability and timing | Statistical method comparison |

Pilot status (23 July 2026):

hammer-v3 completed: 500k steps, stochastic success 1.00, average return 1652.71, approximately 4 h 12 min.

push-wall-v3 is currently training; remaining pilot tasks have not started.

Observed MPS throughput is likely slower than CPU for this small-network, high-frequency SAC workload; a controlled CPU-versus-MPS timing benchmark is planned.

Pilot outputs must not be used as final paper results because task count, training budget, seed count and evaluation protocol differ from the formal design.

# 6. Formal Experiment Plan

| Phase | Workstream | Acceptance criterion |
| --- | --- | --- |
| 1 | Complete pilot | Finish CW5 baseline; validate artifacts and aggregate curves. |
| 2 | Runtime benchmark | Compare CPU and MPS with identical short runs; select formal compute path. |
| 3 | Metric refactor | Store mixed-policy curves for JSRL FT; keep h=0 task-end/final metrics. |
| 4 | Method smoke tests | Run CW10 1k/task for every baseline; verify task changes and checkpoints. |
| 5 | Single-task references | Run CW10 single-task SAC at 1M/task for all formal seeds. |
| 6 | Formal baselines | Run fine-tuning, task-conditioned, PackNet, ClonEx-SAC and WSRL under the same protocol. |
| 7 | Transfer study | Compare WSRL and JSRL variants under identical seeds, task order and evaluation budget. |
| 8 | Forgetting study | Compare fine-tuning, one-hot task conditioning and richer task embeddings if warranted. |
| 9 | Integration ablations | Test only evidence-supported combinations of transfer and forgetting components. |
| 10 | Final method | Freeze the final design and name after transfer, forgetting and interaction results. |
| 11 | Analysis | Report mean and variation across seeds; AP, return, forgetting, FT and per-task curves. |

# 7. Reference Papers and Code

| Reference | Use in this project | Local / official source |
| --- | --- | --- |
| Continual World | Benchmark protocol and official single-task/continual evaluation definitions. | awarelab/continual_world |
| Disentangling Transfer in CRL | ClonEx-SAC paper, appendix and source implementation. | references/disentangling_transfer/ |
| Jump-Start Reinforcement Learning | Two-policy roll-in and backward curriculum. | references/Neurips-2023-jump start RL.pdf |
| Warm-Start Reinforcement Learning | Warm-start policy/value reuse and comparison with JSRL. | references/ICLR-2025-warm start rl.pdf; references/wsrl_code/ |
| PackNet / CRL baseline | Parameter isolation baseline; implementation cross-checked against the CRL reference code. | references/disentangling_transfer/code/ |
| DGCRL | Prior demonstration-guided CRL work and curriculum inspiration. | references/dgcrl.pdf; references/DGCRL-main/ |
| CKA-RL | Recent continual knowledge adaptation reference and modern environment comparison. | references/NeurIPS-2025-continual-knowledge-adaptation-for-reinforcement-learning-Paper-Conference.pdf; references/CKA-RL-main/ |

# 8. Immediate Decisions and Risks

Metric naming: label mixed-policy FT explicitly so reviewers can distinguish direct policy reuse from learner-only transfer.

Guide quality: best return is aligned with ClonEx-SAC, but success-then-return should be considered as an ablation for Meta-World.

Compute: do not extrapolate formal runtime from MPS until the CPU/MPS benchmark is complete.

Reproducibility: freeze task order, seeds, configs and single-task reference curves before formal comparisons.

Method selection: do not label WSRL, JSRL or task conditioning as the final method before ablation evidence is available.

Claims: describe jsrl_continual as a continual adaptation of JSRL, not a reproduction of JSRL's IQL/Qt-Opt experiments.